## Budget_Estimate
Project Budget Estimate
Scenario: Secure Infrastructure Design, Deployment, Defense and Assessment for a Remote-first Startup
Control Inputs
People cost per day (€) | 300
Project duration (days) | 10
Contingency rate | 10%
People Budget
Workstream | Owner / Role | Days | Rate (€ / day) | Cost (€) | Notes
Architecture & technical specification | Project lead / architect | 2 | 300 | 600 | Context, PRD, architecture, risks, controls
Core infrastructure deployment | System & services admin | 3 | 300 | 900 | AD/IAM, web, DB, file-sharing
Network security & remote access | Security admin | 1.5 | 300 | 450 | Firewall, exposure control, VPN
Monitoring, backup & validation | Resilience owner | 1.5 | 300 | 450 | Monitoring, backups, proof collection
Blue Team / Red Team documentation | Security analyst | 1 | 300 | 300
Project management & presentation | Project lead | 1 | 300 | 300 | Kanban, budget, roadmap, final deck
Total people cost |  |  |  | 3000
One-time Setup and Tools
Item | Category | Quantity | Unit Cost (€) | Cost (€) | Notes
VM / hypervisor base images | Lab setup | 1 | 0 | 0 | Uses existing lab or local virtualization
Public domain / DNS setup | Internet-facing setup | 1 | 15 | 15 | Illustrative one-time registration/setup cost
Presentation / documentation assets | Delivery material | 1 | 0 | 0 | Assumes internal tooling
Contingency base for misc. setup | Miscellaneous | 1 | 50 | 50
Total one-time setup cost |  |  |  | 65
Initial Project Budget Summary
People cost |  |  |  | 3000
One-time setup cost |  |  |  | 65
Contingency |  |  |  | 307
Total initial project budget |  |  |  | 3372
Estimated Monthly Run-Rate
Item | Source | Monthly Cost (€) | Annualized (€) | Type | Notes
Cloud / hosting | Internal project assumption | 60 | 720 | Recurring | Infrastructure hosting estimate
Domain / DNS / certificates | Internal project assumption | 15 | 180 | Recurring | Internet-facing service estimate
Monitoring / logging | Internal project assumption | 0 | 0 | Recurring | Assumes open-source self-hosting
Backup storage | Internal project assumption | 20 | 240 | Recurring | Protected backup storage estimate
Total monthly run-rate |  | 95 | 1140
Assumptions and notes
• This budget is an illustrative SME-scale estimate for the CYBFS final project and should be adjusted to the actual lab, hosting, and team context.
• People cost uses the project guide example of 300€/day as a simulation baseline. Source noted in Assumptions sheet.
• Recurring monthly costs are simplified placeholders intended to show budget logic and trends rather than audited vendor pricing.

## Assumptions
Budget Assumptions
All cost assumptions below are editable inputs for the project budget.
Assumption | Value | Explanation | Source
People cost per day (€) | 300 | Guideline from project material for simulated man-day cost. | https://www.jedha.co/
Project duration (days) | 10 | Final project indicative duration in the brief. | https://www.jedha.co/
Contingency rate | 10% | Project buffer for unexpected effort and minor tooling costs. | Internal project assumption
Cloud / hosting monthly estimate (€) | 60 | Illustrative SME-scale monthly infrastructure estimate. | Internal project assumption
Domain / DNS / certificates monthly estimate (€) | 15 | Illustrative recurring internet-facing service estimate. | Internal project assumption
Monitoring / logging monthly estimate (€) | 0 | Assumes open-source stack, self-hosted for MVP. | Internal project assumption
Backup storage monthly estimate (€) | 20 | Illustrative storage estimate for protected backups. | Internal project assumption
Note on B5: https://www.jedha.co/
Note on B6: https://www.jedha.co/
Note on B7: Internal project assumption
Note on B8: Internal project assumption
Note on B9: Internal project assumption
Note on B10: Internal project assumption
Note on B11: Internal project assumption

## Summary
Budget Summary
Metric | Value
One-time people cost | 3000
One-time infrastructure setup | 65
Contingency | 307
Total initial project budget | 3372
Estimated monthly run-rate | 95
Estimated annual run-rate | 1140
Notes
• Initial budget includes people cost, one-time setup items, and contingency.
• Run-rate estimates represent a simple monthly operating view for the MVP environment.
• Values are illustrative and should be adjusted to match actual tooling, hosting, and team choices.