## Risk_Register
Blue Team Risk Register — Case HOME_Run01
Case ID | HOME_Run01
Workstream | Blue Team
Review Type | Defensive review
Environment | SME-scale remote-first startup lab infrastructure
Status | Initial register
Risk ID | Related Finding | Risk Title | Component(s) | Description | Likelihood | Impact | Inherent Score | Inherent Rating | Priority | Owner | Current Status | Existing Controls | Planned Treatment | Target Date | Retest Status | Residual Score | Residual Rating | Evidence Ref
RISK-01 | F01 / F09 | Incomplete Evidence Coverage | Entire infrastructure | Critical controls and validations are documented but not yet fully backed by populated screenshots, outputs, and indexed proof. | High | Medium | 5 | High | Immediate | Project Lead / Documentation Owner | Open | Strong repository structure; evidence folders and indexes already defined. | Replace placeholders with real proof and map each control to evidence. | 2026-04-18 | Not Retested | 5 | High | EV01-EV21
RISK-02 | F02 | Blue Team Case Not Fully Populated | Blue Team case management | Timeline, terrain, and case fields still require real environment values and review observations. | High | Medium | 5 | High | Immediate | Blue Team Analyst | Open | Case structure, scope, and methodology are complete. | Populate all case files with actual hostnames, dates, observations, and evidence links. | 2026-04-18 | Not Retested | 5 | High | Case files
RISK-03 | F03 | Overexposure Until Port and Firewall Proof Exists | Web / Database / Network Security | Restricted exposure is defined in design, but practical proof of allowed and denied network paths is still incomplete. | Medium | High | 5 | High | Immediate | Network & Security Administrator | Open | Firewall strategy, trust boundaries, and validation plan documented. | Capture firewall rules, allowed port proof, denied DB direct access, and blocked unauthorized paths. | 2026-04-17 | Not Retested | 5 | High | NET01-NET10
RISK-04 | F04 | Access Control Not Yet Proven in Practice | AD / IAM / File Server | Identity and permission model is designed, but authorized and unauthorized access behavior still needs proof. | Medium | High | 5 | High | Immediate | System Administrator / Blue Team Analyst | Open | Centralized IAM, groups, and file access model documented. | Run and capture successful authorized access and denied unauthorized access tests. | 2026-04-17 | Not Retested | 5 | High | AD04-AD08; FS06-FS08
RISK-05 | F05 | Backup Without Restore-Oriented Validation | Backup / Monitoring / Database / File Server | Backup logic exists on paper, but resilience remains weak until backup artifacts and a restore-oriented scenario are evidenced. | Medium | High | 5 | High | Immediate | Monitoring & Resilience Owner | Open | Backup scope, DR logic, and validation approach are documented. | Produce one backup artifact and one restore-oriented validation path with proof. | 2026-04-18 | Not Retested | 5 | High | BM06-BM10
RISK-06 | F06 | Monitoring Coverage Not Yet Confirmed | Backup / Monitoring and core services | Monitoring is positioned correctly, but visibility over critical services must be proven to support defensive operations. | Medium | Medium | 4 | Medium | High | Monitoring & Resilience Owner | Open | Monitoring component and proof structure already planned. | Capture dashboard, host visibility, service visibility, and one meaningful event or status view. | 2026-04-17 | Not Retested | 4 | Medium | BM01-BM05
RISK-07 | F07 | Core Service Integration Proof Incomplete | Web / Database / IAM / File Server | Architecture is integrated by design, but end-to-end behavior still requires concrete proof to support Blue Team conclusions. | Medium | Medium | 4 | Medium | High | System Administrator | Open | Integration test cases and architecture paths documented. | Capture web-to-database behavior and IAM-linked file access behavior. | 2026-04-18 | Not Retested | 4 | Medium | TC-INT-01 to TC-INT-03
RISK-08 | F08 | Administrative Access Restriction Needs Proof | IAM / Network Security / critical hosts | Admin access is intended to be restricted, but practical evidence of approved vs unapproved admin paths is still missing. | Medium | Medium | 4 | Medium | High | Network & Security Administrator | Open | Restricted admin logic and network security design documented. | Capture proof of approved admin path and denied unapproved path. | 2026-04-17 | Not Retested | 4 | Medium | NET07, NET10
RISK-09 | F09 | Framework More Mature Than Final Delivery | Entire project / Blue Team contribution | The methodology and structure are strong, but the remaining gap between design quality and completed deliverables affects final defensibility. | High | Medium | 5 | High | Immediate | Project Lead | Open | All folders, templates, and management artifacts are in place. | Finish completion of open placeholders, align findings/risk/remediation/retest, and prepare final summary. | 2026-04-19 | Not Retested | 5 | High | Blue Team dossier
Instructions: update blue input columns only (Likelihood, Impact, Owner, Status, Target Date, Retest Status, Evidence Ref as needed). Formula columns calculate score, rating, and priority automatically.

## Rating_Scales
Label | Value | Residual Score to Rating | Threshold
Low | 1 | Low | 1
Medium | 2 | Medium | 3
High | 3 | High | 5
Scoring note | Inherent score = Likelihood value + Impact value. Residual score reduces when retest status is Resolved or Partially Resolved.

## Summary
Blue Team Risk Register Summary
Total risks | 9 | Component | High | Medium
High inherent risks | 6 | Entire infrastructure | 1 | 0
Medium inherent risks | 3 | Web / Database / Network Security | 1 | 0
Open risks | 9 | AD / IAM / File Server | 1 | 0
Immediate priorities | 6 | Backup / Monitoring / Database / File Server | 1 | 0
Resolved after retest | 0 | Backup / Monitoring and core services | 0 | 1
|  | Web / Database / IAM / File Server | 0 | 1
|  | IAM / Network Security / critical hosts | 0 | 1
Top immediate actions
• Complete real evidence collection across all critical controls.
• Prove access control with authorized and unauthorized user tests.
• Validate restricted exposure with firewall, port, and denied-path proof.
• Produce one backup artifact and one restore-oriented validation path.