## Roadmap_Gantt
Final Project CYBFS — Roadmap & Gantt
10-day execution plan aligned with the official final project timeline
Legend | Planned | In Progress | Done | Blocked
Phase | Task ID | Task | Owner | Priority | Status | Start Day | End Day | Duration | Dependency | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Initiation | PM-01 | Finalize company profile, business context, PRD and MVP | Chris | High | Done | 1 | 2 | 2 | bar: Day 1 to Day 2
Specification | TS-01 | Complete technical specification (architecture, risks, security, backup) | Chris | High | In Progress | 1 | 4 | 4 | PM-01 | bar: Day 1 to Day 4
Deployment | INF-01 | Deploy AD / IAM and test user-group logic | Chris | High | Planned | 2 | 5 | 4 | TS-01 | bar: Day 2 to Day 5
Deployment | INF-02 | Deploy Web Server and validate service availability | Chris | High | Planned | 3 | 5 | 3 | TS-01 | bar: Day 3 to Day 5
Deployment | INF-03 | Deploy Database and validate app connectivity | Chris | High | Planned | 3 | 5 | 3 | INF-02 | bar: Day 3 to Day 5
Deployment | INF-04 | Deploy File Server / Nextcloud and validate access | Chris | High | Planned | 3 | 6 | 4 | INF-01 | bar: Day 3 to Day 6
Security | SEC-01 | Configure firewall, VPN and service exposure controls | Chris | High | Planned | 4 | 6 | 3 | INF-01 | bar: Day 4 to Day 6
Resilience | OPS-01 | Configure monitoring and backup workflow | Chris | Medium | Planned | 5 | 6 | 2 | INF-03 | bar: Day 5 to Day 6
Validation | VAL-01 | Run deployment test cases and collect screenshots / proofs | Chris | High | Planned | 6 | 7 | 2 | INF-01, INF-02, INF-03, INF-04, SEC-01, OPS-01 | bar: Day 6 to Day 7
Blue Team | BT-01 | Complete Blue Team case with findings, remediation and retest | Chris | High | Planned | 7 | 8 | 2 | VAL-01 | bar: Day 7 to Day 8
Red Team | RT-01 | Complete pentest scope, findings, remediation and retest | Chris | High | Planned | 7 | 8 | 2 | VAL-01 | bar: Day 7 to Day 8
Project Mgmt | PM-02 | Finalize Kanban export, roles, retrospective, roadmap and budget | Chris | Medium | In Progress | 8 | 9 | 2 | VAL-01 | bar: Day 8 to Day 9
Delivery | DEL-01 | Write technology watch report and prepare final presentation | Chris | High | Planned | 9 | 10 | 2 | BT-01, RT-01, PM-02 | bar: Day 9 to Day 10
Note on A1: Editable template generated for the CYBFS project roadmap/Gantt.
Note on G4: Use day numbers 1 to 10 to match the official project timeline.

## Milestones
Milestones
Milestone | Target Day | Owner | Status | Deliverable Link | Notes
Context + PRD completed | 2 | Chris | Done | 01_Context_PRD/
Technical specification completed | 4 | Chris | In Progress | 02_Technical_Specification/
Core infrastructure deployed | 6 | Chris | Planned | 03_Infrastructure_Deployment/
Validation + evidence collected | 7 | Chris | Planned | 03_Infrastructure_Deployment/
Blue Team + Red Team completed | 8 | Chris | Planned | 05_Blue_Team/ + 06_Red_Team/
Project management finalized | 9 | Chris | In Progress | 04_Project_Management/
Technology watch + presentation ready | 10 | Chris | Planned | 07_Technology_Watch/ + 08_Final_Presentation/

## How_to_Use
How to use this roadmap
1. Update Owner, Status, Start Day and End Day as the project advances.
2. The Duration column is calculated automatically.
3. The Gantt bar fills automatically from Start Day to End Day.
4. Replace the placeholder 'Chris' with the real owner(s) if needed.
5. You can add rows for extra tasks; copy formulas from an existing row.
6. Recommended evidence: export or screenshot this sheet once mid-project and once before final delivery.
Status colors
Planned
In Progress
Done
Blocked